## Slide 1: Project Proposal Writing
What is Project Proposal?
By: Misganw Aguate
Email: mail@ethioptec.com
Website: https://ethioptec.com or https://info.ethioptec.com

## Slide 2: Proposal Writing
What is a Project Proposal? Project
Project proposals present a project by outlining:
The specific objectives of the project.
The technical approach to be used in solving the problem or developing the product
The anticipated results of the project
Project proposals should answer the following questions:
Is the problem sufficiently important to justify money, time and effort?
Is the project well defined and realistic?
Have you outlined a sound approach, including your ability to perform the tasks?

## Slide 3: Project Proposal Writing
A project proposal can be a selling document written to:
Influence decision-makers.
Convince them to commit time, money or resources in support of a specific project.
A winning proposal addresses an important question with an innovative idea.
well expressed with a clear indication of methods for pursuing the idea, evaluates the findings, and makes them known to all who need to know.
Why Write a Project Proposal? To inform people or organizations of a project that you would like to implement. A project proposal is much like a business plan.
To apply for a grant
To ask for other resources or support from another organization.
To explore the causes of a problem and clearly define next steps in solving that problem.

## Slide 4: Project Proposal Writing
Components of a Project Proposal
Cover Page
Abstract
Introduction
  Antecedents
  History and Definition of the Problem
  Justification and Intervention
Objectives
Intervention Design and Strategy
Activities and Timeline
Budget
Evaluation Indicators
Bibliography
Annex

## Slide 5: Project Proposal Writing
Cover Page
Institution Information • Title (no more than 15 words corresponding to the theme of the intervention) • Author/s • Date Abstract
Abstract means condensate of paper in one paragraph
Start with typically 1-2 sentences on background & aims
Followed by a very short description of what should be done
In the final report of the project bring the main results & major consequences

## Slide 6: Project Proposal Writing
In abstract No figures, no tables, no references (usually), no footnotes, avoid abbreviations, equations and symbols, make sentences short
Abstract should include Introduction, Method, Results and Discussion
Example of Abstract
The extension of the sunspot number series backward in time is of considerable importance for dynamo theory. We have applied a physical model to records of the 10 Be concentration in polar ice to reconstruct sunspot number between the year 850 and the present. The reconstruction shows that the period of high solar activity during the last 60 years is unique throughout the past 1150 years. This nearly triples the interval of time for which such a statement could be made.

## Slide 7: Project Proposal Writing
Introduction • The historical antecedents of the problem and the current situation: Include results or findings of related preliminary studies related to the problem, either national or international. • Description of the problem: Include the description of the current situation and how it got to be that way.

## Slide 8: Project Proposal Writing
• Justification of the Intervention: Clearly define the proposed intervention and justify why this intervention is the best solution to the problem. Objectives • Objectives signify the result that you intend to achieve through the intervention. • They should directly address the problem mentioned in the problem statement Objectives should be SMART:
Specific
Measurable
Achievable
Relevant
Time-bound

## Slide 9: Project Proposal Writing
SMART Process • Specific. Use Specific rather than generalized language; clearly state the issue, the target group, the time and place of the program. • Measurable. Be clear in the objective about what will be changed and by how much. Setting this clearly at the start makes it easier to evaluate. • Achievable. Be realistic about what the program can achieve in terms of the scale/scope of what is being done, the time and resources available. • Relevant. Objectives need to relate to and be relevant to the goals. Remember objectives are the building blocks / steps toward meeting the goals. • Time Specific. Be clear in the objectives about the timeframe in which the program / activities, as well as expected changes, will take place.

## Slide 10: Project Proposal Writing
Intervention Design and Strategy • Describe the intervention, explaining what you propose to do to respond to the problem.
• It is important to remember that the proposed intervention leads to the objectives that were initially proposed. • Intervention design and strategy should be research based
Activities and Timeline • Activities includes specific action items under the intervention design. • All activities should be linked to the objectives.
• Specify:
 Who will do them  When they will be done  How they will be accomplished  Why you choose this approach  How long each activity will take

## Slide 11: Project Proposal Writing
Budget Strategy • Ask for what you need to do the work. • Justify requests that are significant or out of the ordinary. • Develop a budget explanation to delineate clearly how budget figures were computed. Evaluation Indicators • Clear objectives and activities lead to an evaluation plan – how are you going to know you accomplished what you set out to do? • Choose indicators that will tell you whether or not you achieved your goal and met its objectives.

## Slide 12: Project Proposal Writing
Logic Modelsctivities Outputs Indicators • A Logic Model is a widely used tool that presents specific details of program inputs, activities and outcomes, and shows generally how they are related. • Logic Models can be very helpful in organizing and summarizing your information.

## Slide 13: Project Proposal Writing
Bibliography • Cite ALL information and ideas that were not originally yours. • Be consistent

## Slide 14
THANK YOU